## Requirements Tracker
ID | Category | Requirement / Capability | Requirement Details | User Story | Status | Priority | System(s) / Data Source(s) | Notes
REQ-001 | Business Rules & Policies | 30-Day Rehire Policy validation | Validate whether an onboarding worker falls within the 30-day rehire policy window and flag the record for business review when applicable. | As an IAM reviewer, I want the system to flag workers within the 30-day rehire window so that I can prevent processing contracts that require additional review. | Pending | High | Roster Lock, Master Roster, Fieldglass, historical termination data | Business rule must be formally confirmed and documented.
REQ-003 | Business Rules & Policies | Blacklist validation / don't rehire list | Flag users that match blacklist or restricted worker lists during onboarding validation (Roster locks) | As an IAM reviewer, I want blacklisted workers to be flagged automatically so that restricted users are not approved without review. | Pending | High | Roster Lock, Fieldglass, blacklist source | Requires approved blacklist source and access permissions.
REQ-004 | Business Rules & Policies | Duplicate worker detection | Detect duplicate worker submissions or duplicate change requests before processing or publishing updates. | As an administrator, I want duplicate worker records and duplicate requests to be detected so that the same change is not applied multiple times. | Pending | High | Application database, intake files | Unique identifier logic must be defined.
REQ-005 | Business Rules & Policies | Active-worker validation | Validate whether a worker is active across KP systems and vendor sources before approving onboarding or access-related actions. | As an IAM reviewer, I want active-worker status validated across systems so that onboarding and access decisions are based on current worker status. | Pending | High | Fieldglass, AccessNow, Roster Lock, vendor files | Need agreed definition of active worker.
REQ-006 | Business Rules & Policies | NPN validation workflow | Support NPN validation before enrollment; allow validated users to be identified before enrollment is sent to Darlene/evolveNXT. | As an IAM team member, I want NPN validation captured in the roster process so that only validated users are sent for enrollment. | Pending | Low | Roster Lock, NPN validation file | Column/process needs to be added to template and SOP.
REQ-007 | Business Rules & Policies | Contract start/end date validation | Validate contract dates and worker start/end dates from Fieldglass before processing. | As an administrator, I want contract dates validated so that worker records align to active agreements and onboarding dates. | Pending | High | Fieldglass, Roster Lock | Fieldglass report fields must be available.
REQ-008 | Business Rules & Policies | Mandatory field validation | Prevent processing when required intake fields are missing, incomplete, or invalid. | As an IAM requester, I want the system to show missing required fields so that I can correct records before submission. | Pending | High | Roster Lock, Fieldglass imports | Required fields must be defined in data dictionary/template.
REQ-009 | Onboarding Timing Rules | Roster Lock submission deadline validation | Track and validate whether Roster Lock is submitted within the required deadline before onboarding. | As an IAM Team member, I want the system to identify late Roster Lock submissions so that onboarding delays and risk can be addressed. | Pending | High | Roster Lock, onboarding schedule | Current meeting notes reference 5 days before onboarding with a desired extension to two weeks.
REQ-010 | Onboarding Timing Rules | Fieldglass acceptance timing check | Track whether workers are accepted in Fieldglass prior to formal start date. | As an IAM team member, I want Fieldglass acceptance timing visible so that I can identify late or missing entries before onboarding begins. | Pending | High | Fieldglass | Pending to confirm acceptance time frames before formal start.
REQ-011 | Onboarding Timing Rules | Missed milestone alerts | Generate alerts when onboarding records, validations, or approvals miss expected milestone dates. | As an IAM administrator, I want missed milestone alerts so that I can escalate delays before onboarding is impacted. | Pending | Medium | Roster Lock, Fieldglass, workflow tracker | Milestones and SLA thresholds must be defined.
REQ-012 | Source of Truth | Centralized worker source of truth | Create a centralized worker record that consolidates key data from Roster Lock, Master Roster, Fieldglass, Staffing Plan, AccessNow, Salesforce, CXOne, and NICE IEX. | As an IAM leader, I want a centralized source of truth so that worker status and access-related decisions are based on consolidated data. | Pending | High | Roster Lock, Master Roster, Fieldglass, Staffing Plan, AccessNow, Salesforce, CXOne, NICE IEX | Data ownership, field mapping, and source precedence must be defined.
REQ-013 | Source of Truth | Unified worker profile | Maintain a single worker profile with vendor, role, contract, dates, manager/sponsor, worker status, and system readiness information. | As an IAM user, I want one consolidated worker profile so that I do not need to compare multiple reports manually. | Pending | High | Fieldglass, Roster Lock, AccessNow, Master Roster | Field definitions must be aligned.
REQ-014 | Source of Truth | Source precedence rules | Define which system is authoritative for each key field when data conflicts occur. | As an administrator, I want source precedence rules so that conflicting data can be resolved consistently. | Pending | High | All source systems | Requires business alignment across IAM, WFM, and stakeholders.
REQ-016 | Source of Truth | Vendor ownership identification | Capture vendor attribution for each worker to support auditing and reconciliation. | As an IAM team member, I want each worker tied to a vendor so that discrepancies can be assigned and corrected. | Pending | High | Fieldglass, vendor hierarchy files, Roster Lock | Requires consistent vendor identifiers.
REQ-017 | Reconciliation | Roster Lock vs Fieldglass reconciliation | Compare Roster Lock records against Fieldglass records to identify missing, extra, or mismatched workers. | As an IAM analyst, I want Roster Lock and Fieldglass compared automatically so that discrepancies are visible without manual VLOOKUPs. | Pending | High | Roster Lock, Fieldglass | Initial weekly crossmatch was discussed.
REQ-018 | Reconciliation | Roster Lock vs Staffing Plan reconciliation | Compare Roster Lock against the staffing plan to validate expected hires and headcount. | As an IAM analyst, I want Roster Lock compared to staffing plan data so that expected hires align to vendor submissions. | Pending | High | Roster Lock, Staffing Plan | Requires Staffing Plan source and agreed fields.
REQ-019 | Reconciliation | Fieldglass vs AccessNow reconciliation | Compare Fieldglass worker records to AccessNow information to identify access or worker status gaps. | As an IAM analyst, I want Fieldglass compared with AccessNow so that worker access records can be validated. | Pending | Low | Fieldglass, AccessNow | AccessNow data availability and reporting process must be confirmed. (Active worker vs inactive)
REQ-021 | Reconciliation | Vendor discrepancy reporting | Generate a list of discrepancies categorized by vendor, issue type, and action required. | As an IAM analyst, I want discrepancies categorized by vendor so that follow-up can be assigned quickly. | Pending | Medium | All intake and reconciliation sources | Requires discrepancy categories.
REQ-022 | Workflow Automation | Automated Roster Lock ingestion | Detect and ingest Roster Lock files from the shared SharePoint location. | As an administrator, I want Roster Lock files ingested automatically so that manual consolidation is reduced. | Pending | High | SharePoint, Roster Lock | Folder structure and permissions must be finalized.
REQ-023 | Workflow Automation | Automated Fieldglass import | Import Fieldglass reports and allow review of changes before applying them to the database. | As an administrator, I want Fieldglass imports reviewed before publication so that data quality is controlled. | Pending | High | Fieldglass report, SharePoint | Depends on access to complete Fieldglass reports.
REQ-024 | Workflow Automation | File validation before processing | Validate imported files for format, required columns, and duplicated submissions before workflow processing. | As an administrator, I want file validation before processing so that invalid imports do not corrupt the source of truth. | Pending | High | SharePoint, intake templates | Template requirements must be finalized.
REQ-025 | Workflow Automation | Preview changes before publishing | Display proposed changes for administrator review before updating the database. | As an administrator, I want to preview changes before publishing so that I can prevent incorrect updates. | Pending | High | Application database, import files | Part of single-writer controlled update model.
REQ-026 | Workflow Automation | Exception handling for invalid records | Route invalid, conflicting, or incomplete records to an exception or quarantine process. | As an administrator, I want invalid records routed to exception handling so that normal processing can continue safely. | Pending | High | Application workflow | Exception categories must be defined.
REQ-027 | Workflow Automation | Template-based imports | Use controlled intake templates to standardize imports and reduce data variation. | As an IAM requester, I want standardized templates so that submissions are complete and consistent. | Pending | Medium | Roster Lock template, Fieldglass report | Template and data dictionary alignment required.
REQ-028 | Review & Approval | Under Review status | Include an Under Review status for records requiring business validation before approval or rejection. | As an IAM analyst, I want records to move into Under Review status so that business cases can be assessed before processing. | Pending | High | Application workflow | Business logic cases must be documented.
REQ-029 | Review & Approval | Approval and rejection workflow | Allow authorized users to approve or reject requests and record the decision. | As an IAM Analyst, I want to approve or reject requests so that each decision is traceable and controlled. | Pending | High | Application workflow | Decision reasons should be captured.
REQ-030 | Review & Approval | Quarantine workflow | Place conflicting or disputed changes into quarantine until an authorized decision is made. | As an administrator, I want conflicting records quarantined so that updates are not overwritten or corrupted. | Pending | High | Application workflow, database | Requires conflict resolution criteria.
REQ-031 | Review & Approval | Multiple request states | Support statuses such as Approved, Rejected, Pending, Under Review, Quarantine, and Published. | As an IAM analyst, I want request statuses visible so that I can understand where each item is in the process. | Pending | Medium | Application workflow | Status naming must align to business process.
REQ-032 | Change Management | Single-writer model | Ensure only one authorized administrator can apply approved changes directly to the database. | As an admin, I want a single-writer model so that database updates remain controlled and auditable. | Pending | High | Application database | Discussed as a security and data integrity control.
REQ-033 | Change Management | Draft vs Published states | Separate draft/imported changes from published database records until approval is complete. | As an administrator, I want draft and published data separated so that unapproved changes do not affect the source of truth. | Pending | High | Application database | Publication flow must be designed.
REQ-034 | Change Management | Version control for updates | Maintain versions of changes, publications, and database snapshots for rollback and audit. | As an auditor, I want version history so that I can see what changed and when. | Pending | High | Application database, SharePoint | Requires snapshot storage and retention policy.
REQ-035 | User Roles & Security | Requester role | Allow requesters to submit requests and verify workflow behavior without direct database write access. | As a requester, I want to submit requests safely so that changes can be reviewed before they are applied. | Pending | Medium | Application | Role permissions must be finalized.
REQ-036 | User Roles & Security | Reviewer role | Allow reviewers to validate information and recommend approval, rejection, or quarantine. | As a IAM Analyst , I want access to review records so that business validations can be completed before approval. | Pending | High | Application | Role permissions must be finalized.
REQ-037 | User Roles & Security | Administrator role | Allow administrators to import, approve, reject, publish, recover, and maintain data according to permissions. | As an administrator, I want controlled administrative permissions so that I can safely manage the application and database. | Pending | High | Application, database, SharePoint | Administrative responsibilities must be documented.
REQ-038 | User Roles & Security | Auditor role | Allow auditors to review actions, decisions, and logs without changing data. | As an IAM Analyst, I want read-only audit access so that I can verify compliance without modifying records. | Pending | High | Audit logs, application database | Read-only access model required.
REQ-039 | User Roles & Security | Master Admin role | Maintain a master/system admin role for application-level configuration, user management, and technical control. | As a system owner, I want a master admin role so that application configuration and technical support can be controlled. | Pending | Medium | Application | Separation from business administrator should be defined.
REQ-040 | User Roles & Security | Temporary delegated permissions | Allow limited temporary permissions where needed for continuity, with traceability. | As an administrator, I want temporary delegated access so that operations can continue during absences while maintaining traceability. | Pending | Medium | Application | Delegation duration and approval rules needed.
REQ-041 | User Roles & Security | Dual authentication | Require application authentication and Windows/user validation before allowing access. | As a system owner, I want dual authentication so that only authorized users can operate under their own identity. | Pending | High | Application, Windows credentials | Authentication method must be validated with IT/security.
REQ-042 | Audit & Governance | Immutable audit logs | Create immutable logs for requests, changes, decisions, approvals, and publication events. | As an auditor, I want immutable logs so that historical actions cannot be altered after the fact. | Pending | High | Application, SharePoint | Storage and retention policy needed.
REQ-043 | Audit & Governance | User/device/timestamp tracking | Record user, device, and timestamp for each access, action, and attempted change. | As an auditor, I want user, device, and timestamp tracking so that accountability is clear for every action. | Pending | High | Application logs | Must align with security expectations.
REQ-044 | Audit & Governance | Decision history | Capture the decision history for approvals, rejections, quarantine actions, and recovered records. | As an IAM lead, I want decision history so that business outcomes are traceable. | Pending | High | Application workflow | Decision reason codes may be needed.
REQ-045 | Audit & Governance | Data lineage tracking | Track the source of each key data element and how it entered the source of truth. | As an IAM Analyst, I want data lineage so that discrepancies can be traced back to their source. | Pending | Medium | All source systems | Requires data mapping and source tracking.
REQ-046 | SLA & Notifications | SLA definitions by process type | Define SLA expectations and due dates by request/process type. | As an IAM lead, I want SLA targets by process type so that performance and escalations can be managed. | Pending | Medium | Application workflow | SLA targets must be agreed.
REQ-047 | SLA & Notifications | SLA countdown and aging tracking | Track request age and SLA countdown similar to operational ticketing expectations. | As an IAM administrator, I want SLA aging visible so that at-risk requests can be prioritized. | Pending | Medium | Application workflow | Requires SLA configuration.
REQ-048 | SLA & Notifications | Escalation notifications | Send escalation notifications when pending items or SLA risks require action. | As an IAM lead, I want escalation alerts so that delayed items are addressed before they become risks. | Pending | Medium | Application workflow, email/Teams notification | Escalation path must be defined.
REQ-049 | SLA & Notifications | Validation failure notifications | Notify responsible users when file imports or worker validations fail. | As a requester, I want validation failure notifications so that I can correct issues quickly. | Pending | Medium | Application notification engine | Notification channel must be determined.
REQ-050 | Reporting & Dashboard | Executive dashboard | Provide leadership visibility into onboarding status, active workers, offboarding status, vendor metrics, SLA compliance, exceptions, and reconciliation. | As a leader, I want an executive dashboard so that I can monitor IAM automation and governance outcomes. | Pending | High | All source systems | Dashboard scope and metrics must be confirmed.
REQ-051 | Reporting & Dashboard | Operational dashboard | Provide daily/weekly operational views of pending, blocked, in-progress, and completed workflow items. | As an IAM administrator, I want operational dashboard views so that I can manage workload and follow-ups. | Pending | Medium | Application workflow | Status definitions must be finalized.
REQ-052 | Reporting & Dashboard | Weekly reconciliation report | Produce a weekly reconciliation report comparing Roster Lock, Fieldglass, staffing plan, and headcount. | As an IAM analyst, I want a weekly reconciliation report so that discrepancies are reviewed on a regular cadence. | Pending | Low | Roster Lock, Fieldglass, Staffing Plan, headcount | Smartsheet/template approach was discussed.
REQ-053 | Reporting & Dashboard | Offboarding compliance report | Track terminations and offboarding compliance, including delays that may create access risk. | As an IAM leader, I want offboarding compliance reporting so that access termination risks can be monitored. | Pending | High | AccessNow, Fieldglass, offboarding Power BI, ServiceNow | 48-hour compliance monitoring was discussed in the team touchpoint.
REQ-054 | Data Management | Automatic backups | Create backups before applying approved changes or publishing database updates. | As an administrator, I want automatic backups so that data can be restored if an update fails. | Pending | High | Application database, SharePoint | Retention and storage capacity need to be defined.
REQ-055 | Data Management | Snapshot before publication | Generate a database snapshot before changes are published. | As an administrator, I want a snapshot before publication so that prior versions can be restored if needed. | Pending | High | Application database | Owner and timestamp should be included.
REQ-056 | Data Management | Recovery functionality | Allow approved administrators to recover and review prior backups or snapshots. | As an administrator, I want recovery functionality so that I can restore data after errors or conflicts. | Pending | High | Application database, backups | Recovery permissions must be restricted.
REQ-057 | Data Management | Concurrency conflict handling | Detect simultaneous or conflicting changes and prevent unsafe direct writes. | As a system owner, I want concurrency conflict handling so that simultaneous updates do not corrupt data. | Pending | High | Application database | Optimistic concurrency and quarantine logic discussed.
REQ-058 | Integration | SharePoint folder structure | Use a controlled SharePoint folder structure for imports, backups, templates, audit files, and requests. | As an administrator, I want a controlled folder structure so that files are organized and access is managed. | Pending | High | SharePoint | Sofia action item to create/share folder.
REQ-060 | Integration | AD/Azure dependency assessment | Assess whether AD/Azure connection is needed for the automation workflow or ServiceNow integration. | As a technical lead, I want AD/Azure dependencies identified so that architecture decisions are accurate. | Pending | Low | AD/Azure, ServiceNow | Listed as an open technical question in CPS planning artifact.
REQ-061 | Integration | Salesforce profile creation workflow | Support Salesforce profile creation as part of the automation workflow requirements. | As an IAM analyst, I want Salesforce profile creation tracked so that system access readiness is visible during onboarding. | Pending | High | Salesforce, AccessNow | Included in project scope and planning.
REQ-062 | Integration | CXOne profile creation workflow | Support CXOne profile creation and tracking as part of IAM scope. | As an IAM analyst, I want CXOne profile creation tracked so that agent enablement is coordinated with onboarding. | Pending | High | CXOne | Mentioned in IAM Automation weekly update notes and project scope.
REQ-063 | Integration | NICE IEX configuration tracking | Track NICE IEX configuration/build activities as part of automation implementation. | As an IAM analyst, I want NICE IEX configuration tracked so that onboarding readiness can be monitored. | Pending | Medium | NICE IEX | Included in project plan and scope.
REQ-064 | Future Enhancement | SQL backend migration option | Allow future migration from SharePoint/database file structure to SQL Server if the application scales. | As a system owner, I want a future SQL migration path so that the solution can scale without major redesign. | Pending | Low | SQL Server, application database | Future-state concept discussed, not MVP.
REQ-065 | Future Enhancement | Web-based interface | Use or preserve a web-based interface approach to support scalability and future server migration. | As a user, I want a web interface so that the application can scale and be maintained more easily. | Pending | Medium | Application UI | Meeting notes indicate web interface supports scalability.
REQ-066 | Future Enhancement | Workflow orchestrator | Consider a workflow orchestrator if multi-user scale or more complex workflows are needed. | As a system owner, I want orchestrated workflows so that complex approvals and system interactions can scale. | Pending | Low | Future architecture | Future-state concept discussed.
Note on F1: Use the dropdown to select: Pending, In Progress, Completed, Blocked, Dependency, or Cancelled.

## Status Summary
Status | Count
Pending | 62
In Progress | 0
Completed | 0
Blocked | 0
Dependency | 0
Cancelled | 0
Total | 62
Priority | Count
High | 41
Medium | 15
Low | 6

## Source Notes (hidden)
Source Reference | What it supports
turn1search17 | IAM Automation Touchpoint 2026-07-23: Fieldglass reports, roster lock crossmatch, onboarding timing, app setup, user roles, workflow, backlog, SLA/notifications, backups.
turn1search19 | IAM Automation Touchpoint 2026-07-22: roles, approvals, JSON requests, SharePoint, single-writer model, quarantine, backups, authentication, rehire/blacklist validations, technical requirements.
turn1search9 | IAM Automation weekly update chat: 30 day rehire policy, CX1 profile creation, IAM scope, roster locks/staffing plan report, inactivity alert note.
turn1search3 | Source of Truth/Agent Data Discussion: source of truth open issues, Fieldglass/AccessNow findings, hierarchy, active-worker validation, reconciliation.
turn1search8 | IAM Team chat: Roster Lock storage, NPN validation workflow, SOP update, validation complete column/process.
turn1search13 | IAM Team Touchpoint transcript: centralization rationale, AccessNow/Fieldglass reconciliation, auditing/offboarding compliance, ServiceNow process.
turn1search27 | IAM Automation Initiative Project Plan: design, workflow requirements, roster lock template, UAT, communication plan, implementation timeline references.
turn1search28 | IAM Automation Project Charter: scope, source of truth, centralized data ingestion, alerts, workflows, system scope.
turn1search34 | IAM Automation Initiative CPS: ServiceNow, AD/Azure, queue, configuration and workflow planning questions.
turn1search7 | WFM + IAM chat: architecture brief and diagrams including single-writer, request flow, audit event, backup/recovery, duplicate prevention, migration architecture.
turn1search11 | IAM Automation Touchpoint recording reference used for SLA/notification/backlog support from meeting recap context.