Agent Onboarding & Creation Workflow
Quantified ROI Analysis | Money, Time, Capacity, Error Reduction, and Governance Impact

Prepared for WFM / Access Management / NICE IEX Implementation
Date: 2026-06-01

# Workflow Diagram

Figure 1. Current end-to-end onboarding workflow used as the process basis for this analysis.

# 1. Executive Summary

This document expands the current onboarding workflow into a quantified business case. It combines the current end-to-end process design (vendor roster lock to SharePoint ingestion to Power Automate to validation to Fieldglass to NUID to master roster to NICE IEX profile creation) with internal WFM automation benchmarks that already demonstrated measurable financial and capacity benefits in production. Where an exact value for this specific onboarding workflow is not documented in the available source material, the document labels the figure as a modeled estimate or as a benefit-tracking metric that should be measured during rollout.

## Quantified headline values (internal benchmark data and transparent calculations):

| Metric | Conservative | Higher-Value | Classification |
| --- | --- | --- | --- |
| Investment benchmark | $10,565 | $10,565 | Internal benchmark from a live WFM automation solution |
| Annual savings | $22,500 | $30,000 | Internal benchmark |
| Hours saved per analyst per year | 375 | 500 | Internal benchmark |
| Hours saved for 3-person team | 1,125 | 1,500 | Calculated from benchmark |
| Equivalent positions (FTE at 2,080 hrs/year) | 0.54 FTE | 0.72 FTE | Calculated from benchmark |
| Year 1 ROI | 94% | 165% | Internal benchmark |
| Payback period | ~6 months | ~4 months | Internal benchmark |
| 3-year net benefit | $50,935 | $73,435 | Internal benchmark |
| Manual WFM process reduction | 40%+ | 40%+ | Internal benchmark |
| Recovered productive hours | 4,100+ hrs / quarter | 4,100+ hrs / quarter | Internal benchmark from staffing optimization case |

Interpretation: if the onboarding workflow achieves even the conservative end of the internal WFM automation benchmark, the organization recovers more than one thousand hours per year for a 3-person analyst team and effectively frees between 0.54 and 0.72 full-time equivalent capacity without adding headcount.

# 2. Process Basis Used for This ROI

The current process design reflected in the workflow and meeting notes is based on the following logic:

The vendor sends roster information that is placed in a SharePoint folder.

The folder triggers an automated flow that updates the SharePoint roster and sends alerts in parallel to the teams responsible for profile creation.

A human validation checkpoint remains mandatory because automation does not eliminate the need to verify completeness and format correctness.

The workflow is intended to support larger groups (for example classes of 15–20 people) instead of repeated fully manual profile setup.

The process objective is to keep an accurate headcount and support centralized ownership rather than fragmented ownership.

Operational controls visible in the workflow design include:

Standardized roster template usage

Validation for completeness and correct structure

Duplicate prevention

Records archived rather than deleted

Parallel alerts plus data update

Central monitoring and governance

# 3. Roles, Responsibilities, and Economic Ownership

| Role / Team | Primary responsibility | Economic impact owner | Why it matters financially |
| --- | --- | --- | --- |
| KP WFM | Demand planning, governance, validation, monitoring, KPI ownership | Owns benefit realization | Controls how capacity savings are converted into labor value, service stability, and reduced rework |
| HCL WFM | IEX configuration, standards enforcement, centralized model | Owns standardization benefit | Reduces variation, duplicate work, and shadow-tool cost |
| Vendor teams | Roster submission and upstream data quality | Primary source of avoidable defects | Poor data quality creates delays, rework, and configuration defects |
| IAM / Access Management | Worker creation, profile provisioning, access readiness | Owns cycle-time impact | Faster provisioning reduces start delays and operational friction |
| IT / Systems / Power Platform | Automation, integrations, logging, support | Owns technical efficiency | Stable automation lowers recurring manual labor and defect correction work |
| NICE IEX / Platform team | Configuration, entity setup, profile ingestion | Owns platform enablement | Correct setup is required before bulk creation can scale safely |

# 4. Quantified ROI by Benefit Category

## 4.1 Labor Time Savings

Internal WFM automation results already documented in production show 375–500 hours saved per analyst per year and direct annual savings of $22,500–$30,000 for a 3-person team. Using the same benchmark logic, a 3-person onboarding/administrative analyst team would recover 1,125–1,500 hours per year. Using a standard 2,080-hour work year, that equals 0.54–0.72 FTE of capacity released for higher-value work.

| Benefit item | Value | How computed | Use in this document | Evidence type |
| --- | --- | --- | --- | --- |
| Hours saved per analyst/year | 375–500 | Documented benchmark | Direct benchmark for repetitive manual work removal | Internal benchmark |
| Team hours saved/year (3 analysts) | 1,125–1,500 | 375–500 × 3 analysts | Modeled capacity for a small WFM admin team | Calculated from benchmark |
| Equivalent FTE capacity | 0.54–0.72 | team hours ÷ 2,080 | Position-equivalent capacity released | Calculated from benchmark |
| Direct annual dollar savings | $22,500–$30,000 | Documented benchmark | Conservative to higher-value scenario | Internal benchmark |

## 4.2 Position / Capacity Impact

The workflow does not require headcount elimination to create value. The more defensible business case is capacity recovery: the time returned from manual file intake, repeat copy/paste profile creation, error correction, and follow-up coordination can be redeployed to analytics, governance, control, and vendor management. At benchmark performance, the recovered capacity is equivalent to approximately 0.54–0.72 FTE for a 3-person team.

| Capacity impact type | Conservative | Higher-value | Notes |
| --- | --- | --- | --- |
| Recovered analyst days/year | 141 | 188 | Assumes 8-hour workday |
| Recovered work weeks/year | 28.1 | 37.5 | Assumes 40-hour workweek |
| Equivalent FTE | 0.54 | 0.72 | Assumes 2,080 hours/FTE/year |
| Recommended use of released capacity | QA, governance, analytics | QA, governance, analytics + intraday control | Recommended redeployment, not headcount elimination |

## 4.3 Error Reduction and Rework Avoidance

Available internal sources explicitly document reduced risk of human error and rework, standardized data validation, and the need for a validation checkpoint because automation still requires review. However, the sources do not provide a numeric defect-rate baseline for this specific onboarding workflow. For that reason, the financial effect of error reduction is directionally positive and operationally important, but exact dollar savings from avoided onboarding defects must be measured during rollout rather than claimed upfront.

| Error category | What the workflow changes | Expected effect | Quantified now? | Measurement recommendation |
| --- | --- | --- | --- | --- |
| Missing mandatory fields | Standard template + validation checkpoint | Prevents incomplete submissions from moving downstream | No exact baseline available | Track # of rejected files and correction cycle time |
| Wrong file structure / formatting | Automation trigger + validation rules | Reduces downstream processing failures | No exact baseline available | Track # of format failures per month |
| Duplicate identity / profile creation | Duplicate prevention + master roster governance | Avoids cleanup effort and reporting distortion | No exact baseline available | Track # of duplicate records prevented / corrected |
| Late access / profile creation | Parallel alerting to responsible teams | Reduces waiting time between intake and provisioning | No exact baseline available | Track cycle time from file receipt to profile readiness |
| Roster-to-system mismatch | Master roster + enrichment + centralized ownership | Improves data consistency across SharePoint, Fieldglass, and IEX | No exact baseline available | Track variance between roster, worker record, and final profile |

## 4.4 Governance and Shadow-Process Cost Avoidance

The internal IEX go-live plan explicitly states that no parallel WFM tools will be permitted post go-live, and it identifies vendor resistance, missing/dirty roster data, and lack of dedicated WFM points of contact as material risks. While the document does not attach a specific dollar value to eliminating shadow tools, the economic benefit is real: less duplicate reporting, fewer local workarounds, lower reconciliation overhead, and stronger auditability.

Economic effect: lower recurring coordination friction and lower reconciliation effort.

Operational effect: one system of record supports cleaner scheduling, forecasting, and reporting.

Compliance effect: centralized ownership improves audit readiness and defensibility.

# 5. Investment, Payback, and Multi-Year Value

A live WFM automation benchmark documented an investment of $10,565, a payback period of approximately 4–6 months, year-1 ROI of 94%–165%, and a 3-year net benefit of $50,935–$73,435. Those values should be treated as an internal benchmark for the economic profile of WFM automation rather than as a guaranteed project quote for this onboarding workflow. They are still highly relevant because they show the order of magnitude of value that similar automation has already produced inside the same broader WFM context.

| Financial metric | Conservative benchmark | Higher-value benchmark | Use guidance |
| --- | --- | --- | --- |
| Implementation / development investment | $10,565 | $10,565 | Use as internal benchmark unless a dedicated project estimate is approved |
| Annual savings | $22,500 | $30,000 | Strong directional reference for WFM automation value |
| Year-1 ROI | 94% | 165% | Useful executive benchmark |
| Payback period | ~6 months | ~4 months | Useful finance benchmark |
| 3-year net benefit | $50,935 | $73,435 | Longer-term business case reference |

# 6. Workflow-Specific Value Mapping

| Workflow step | Primary benefit driver | Time impact | Dollar impact | Why it matters |
| --- | --- | --- | --- | --- |
| Vendor roster lock submission | Standardized intake | Less follow-up for missing data | Indirect; reduces rework | Higher data consistency before processing |
| SharePoint ingestion | Automatic file landing in one source | Eliminates manual re-entry into tracking lists | Indirect labor reduction | Creates a single starting point for processing |
| Power Automate trigger | Automatic processing and alerting | Removes repetitive admin steps | Direct labor-saving driver | Key source of recurring efficiency |
| Parallel update + alert path | No serial waiting for basic notifications | Shorter cycle time | Indirect labor and delay reduction | Accelerates handoff to IAM / WFM |
| Validation checkpoint | Catch defects early | Avoids downstream cleanup | Avoided rework cost | Protects profile build quality |
| Fieldglass + NUID creation | Formal worker identity path | Reduces ambiguity and manual cross-checking | Avoided rework cost | Necessary for clean master roster creation |
| Master roster | One governed dataset | Reduces reconciliation work | Recurring labor avoidance | Improves downstream scheduling and reporting quality |
| Bulk onboarding in IEX | Scales creation for classes of 15–20 | Higher throughput than repeated manual setup | Strong direct labor-saving driver | Best candidate for repeatable annual savings |
| Governance & monitoring | Less drift, fewer workarounds | Reduces firefighting | Indirect but material | Protects benefits from eroding over time |

# 7. KPI and Benefit-Tracking Framework

To convert the modeled business case into a measured business case, the following KPIs should be tracked from day 1 of pilot and then monthly after go-live:

| KPI | Definition | Baseline needed? | Financial linkage | Recommended owner |
| --- | --- | --- | --- | --- |
| Cycle time to profile readiness | Time from vendor file receipt to profile created / ready | Yes | Faster readiness reduces paid non-productive waiting and admin effort | WFM + IAM |
| Rejected roster files | Count of files rejected for missing data or bad format | Yes | Lower count means less rework and fewer delay costs | Vendor + WFM |
| Duplicate records prevented/corrected | Count of duplicate identity or profile issues | Yes | Lower cleanup effort and lower reporting distortion | IAM + WFM |
| Manual touchpoints per onboarding cohort | Count of human processing steps required | Yes | Direct driver of labor savings | WFM process owner |
| Profiles created per admin hour | Throughput rate for setup activity | Yes | Direct productivity metric | WFM / IAM |
| SharePoint-to-master-roster variance | Mismatch count between staging and mastered records | Yes | Lower reconciliation effort and stronger trust in data | Data governance owner |
| Profile creation defect rate | Errors found after account/profile setup | Yes | Direct rework and access-delay cost | IAM / QA |
| Vendor correction SLA compliance | Percent of corrections returned within target SLA | Yes | Protects schedule and go-live date | Vendor owner |

# 8. Executive Readout

This workflow is financially credible because similar WFM automation already produced documented savings of $22,500–$30,000 per year with 94%–165% year-1 ROI and 4–6 month payback.

The most defensible position-based value is capacity recovery, not position elimination: 1,125–1,500 hours per year for a 3-person admin/analyst team, equivalent to 0.54–0.72 FTE.

The workflow likely creates additional value through avoided errors, avoided duplicate records, and faster provisioning, but those amounts should be measured during rollout because the current source set does not provide a numeric defect baseline.

Centralized governance, one source of truth, and removal of shadow tooling protect the savings and make the process more audit-ready.

# 9. Source Notes and Evidence Classification

The document uses three evidence classes so leadership can distinguish facts from calculations and implementation recommendations:

Documented benchmark: directly stated in internal source material.

Calculated from benchmark: arithmetic performed from a documented internal benchmark (for example team hours or FTE equivalent).

Measurement recommendation: important impact area identified in source material, but no exact numeric baseline was available in the sources reviewed.

| Source | What it supported | Reference ID |
| --- | --- | --- |
| WFM Helper Suite - Executive Report | Investment, annual savings, ROI, payback, time savings per analyst, 45–60 minute manual extraction benchmark | turn8search42 / turn8search43 |
| WFM Key Wins, Impact, and Auto | 40%+ manual process reduction, 4,100+ productive hours recovered in one quarter, 16+ LOBs, recurring savings framing | turn8search46 |
| WFM & Access Management Workflow Alignment transcript | SharePoint folder, automatic flow, parallel alerts, review checkpoint, classes of 15–20, centralized ownership preference | turn8search53 |
| Roster Lock Template | Required onboarding fields | turn8search45 |
| IEX WFM plans and RAID materials | Centralized model, no parallel tools, go-live timing, risk register, governance cadence, data-quality risk | turn8search51 / turn8search60 / turn8search62 / turn8search65 |

# Appendix A. Calculation Logic Used in This Document

Team hours saved = hours saved per analyst × 3 analysts.

Equivalent FTE = team hours saved ÷ 2,080 hours.

Recovered analyst days = team hours saved ÷ 8.

Recovered analyst weeks = team hours saved ÷ 40.

| Calculation | Formula | Result |
| --- | --- | --- |
| Team hours saved (low) | 375 × 3 | 1,125 hours |
| Team hours saved (high) | 500 × 3 | 1,500 hours |
| Equivalent FTE (low) | 1,125 ÷ 2,080 | 0.54 FTE |
| Equivalent FTE (high) | 1,500 ÷ 2,080 | 0.72 FTE |
| Recovered analyst days (low) | 1,125 ÷ 8 | 141 days |
| Recovered analyst days (high) | 1,500 ÷ 8 | 188 days |

# 10. Grounded Implementation Work Plan

This implementation plan translates the updated Agent Onboarding & Creation Workflow into a 60-hour MVP delivery backlog. The plan is sized for 4 hours per day, 5 days per week, across 3 weeks. It includes programming, template verification, Excel and Fieldglass ingestion, exports to downstream templates, CRUD workflows, approvals, audit/bitacora controls, integration testing, failure testing, and user acceptance testing.

Architecture alignment: the updated delivery model follows the workflow from demand planning and roster lock through SharePoint ingestion, validation, Fieldglass worker creation, master roster creation, NICE IEX configuration, agent creation, post-onboarding management, and monitoring/governance. Access remains the controlled master snapshot, and ordinary users do not write directly to the published database.

## 10.1 Delivery Capacity

| Duration | 3 weeks |
| --- | --- |
| Work rhythm | 4 hours/day, 5 days/week |
| Total capacity | 60 hours |
| Runtime constraint | Python 3.10 compatible implementation |
| Delivery posture | MVP with integration tests, failure tests, UAT, and handoff documentation |

## 10.2 Smartsheet / Kanban Work Items

Use the following rows as Smartsheet Kanban cards. Recommended columns: Backlog, Ready, In Progress, Validation, Testing, UAT, Done, and Blocked.

### Week 1 - Foundation

| ID | Phase | Deliverable | Work Item | Hours | Done When |
| --- | --- | --- | --- | --- | --- |
| 1 | Phase 0-2 | Scope & Architecture Baseline | Confirm updated end-to-end workflow, MVP boundaries, Python 3.10 constraint, SharePoint folder model, and single-writer/no-direct-client-write rule. | 2 | Architecture notes match the new onboarding flow and identify source of truth, owners, and constraints. |
| 2 | Phase 2 | Configuration & SharePoint Paths | Define runtime config for incoming roster, templates, pending requests, imported, quarantine, exports, archive, manifests, and Access snapshot folders. | 2 | Config validates all required paths and reflects the SharePoint route used by the automation. |
| 3 | Phase 1, 4, 6, 7 | Template Inventory & Verification | Review roster lock, Fieldglass, NICE IEX, and agent creation templates; record required sheets, headers, mandatory fields, owner, and validation rules. | 4 | Template inventory and validation checklist are complete enough to drive ingestion/export coding. |
| 4 | Phase 5, 9 | Access & Master Roster Data Model | Finalize Access schema for employees, workers, roles, approvals, requests, audit events, batches, versions, vendors, LOBs, skills, mappings, export runs, and agent lifecycle. | 3 | Data model supports roster conversion, NUID tracking, post-onboarding updates, audit, and governance. |
| 5 | Phase 1-3 | Excel Ingestion Foundation | Build reusable Excel reader/validator for roster files and templates using OpenPyXL. | 4 | Reads configured workbook, sheet, and header layouts; returns normalized rows plus row-level validation errors. |
| 6 | Phase 1-4 | Fieldglass Ingestion POC | Ingest roster lock/Fieldglass-ready Excel input into normalized staging data. | 3 | Sample input produces validated staging records for worker creation and master roster updates. |
| 7 | Phase 3, 9 | User Validation & Roles | Implement Windows username capture and role validation for requester, reviewer, writer/admin, auditor, and monitor roles. | 2 | Unauthorized users are blocked and role permissions are enforced before workflow actions run. |

Week 1 - Foundation capacity: 20 hours.

### Week 2 - Core Workflow

| ID | Phase | Deliverable | Work Item | Hours | Done When |
| --- | --- | --- | --- | --- | --- |
| 8 | Phase 8 | CRUD Request Workflows | Implement create, update, deactivate, and view/search workflows as immutable request-driven operations for agent lifecycle changes. | 4 | CRUD actions generate valid requests and never directly modify the master Access snapshot. |
| 9 | Phase 2-3 | Admin Import, Idempotency & Quarantine | Import pending requests and inbound files, detect duplicates, maintain processed registry, and quarantine invalid inputs. | 3 | Duplicate request/file IDs are rejected safely; malformed files move to quarantine with reason captured. |
| 10 | Phase 3-4 | Approval Workflow | Implement review, approve, reject, conflict, and decision notes for onboarding and post-onboarding requests. | 3 | Reviewer/admin decisions are recorded; segregation rules prevent unauthorized self-approval when enabled. |
| 11 | Phase 4-5 | Apply Approved Changes | Apply approved requests to a local Access working copy with record-version checks, referential validation, NUID fields, and status transitions. | 4 | Matching versions apply; stale versions become conflicts; invalid references fail cleanly. |
| 12 | Phase 5 | Master Roster Creation & Enrichment | Convert validated Fieldglass/onboarding data into the official master roster and enrich NUID, status, training/nesting/production, and timeline indicators. | 2 | Master roster records are generated or updated with required enrichment fields. |
| 13 | Phase 4, 9 | Audit / Bitacora | Write audit events for ingest, validation, request creation, approval, rejection, apply, conflict, export, publish, failure, and recovery. | 2 | Audit records include actor, role, computer, request ID, batch ID, entity, result, timestamp, and error details. |
| 14 | Phase 4, 7 | Fieldglass Worker Creation / Export | Generate the Fieldglass worker creation or load file from approved/applied data using configured template mappings. | 2 | Output workbook preserves template structure and passes required-field/header validation. |

Week 2 - Core Workflow capacity: 20 hours.

### Week 3 - Validation, UAT & Handoff

| ID | Phase | Deliverable | Work Item | Hours | Done When |
| --- | --- | --- | --- | --- | --- |
| 15 | Phase 6-7 | NICE IEX Configuration & Agent Creation Package | Generate or scaffold NICE IEX hierarchy/profile export package from master roster data, including vendor, LOB, skills, queues, and configuration rules. | 3 | NICE IEX package is generated or documented with exact blockers and required manual fields. |
| 16 | Phase 8-9 | Snapshot Publication, Recovery & Governance | Implement versioned Access snapshot publication, checksum/manifest, archive rules, failed-batch recovery, and reconciliation report. | 3 | Publish creates versioned snapshot and manifest; failed batches can be retried without duplicate application. |
| 17 | All phases | Integration Tests | Test happy path from roster intake through validation, Fieldglass, master roster, IEX package/export, audit, and publication. | 4 | End-to-end scenario passes with repeatable sample data. |
| 18 | All phases | Failure & Security Tests | Test bad Excel, missing headers, duplicate file/request, unauthorized user, stale version, failed export, checksum mismatch, and recovery. | 3 | Failures route to expected status/folder and produce audit events with actionable error details. |
| 19 | Phase 0-9 | User Acceptance Testing | Run UAT with WFM/requester, vendor input, IAM/access management, KP approver, admin/writer, and auditor/monitor scenarios. | 4 | UAT checklist is completed; defects and follow-up items are logged and prioritized. |
| 20 | Phase 9 | Documentation, Demo & Handoff | Update user/admin/recovery docs, template mapping notes, test evidence, known risks, and final demo package. | 3 | Handoff package is ready and Smartsheet/Kanban items can be closed or moved to next-phase backlog. |

Week 3 - Validation, UAT & Handoff capacity: 20 hours.

## 10.3 Weekly Milestones

End of Week 1: Foundation complete: SharePoint paths, template inventory, Access/master roster model, Excel ingestion foundation, Fieldglass ingestion POC, and user/role validation.

End of Week 2: Core workflow complete: request-driven CRUDs, admin import, idempotency, quarantine, approvals, application into Access working copy, master roster enrichment, bitacora, and Fieldglass output.

End of Week 3: MVP validated: NICE IEX package/export, snapshot publication, recovery/reconciliation, integration tests, failure tests, UAT, documentation, and demo package.

## 10.4 Definition of Done

Code runs on Python 3.10.

SharePoint/OneDrive paths are validated and reflected in runtime configuration.

Roster lock, Fieldglass, NICE IEX, and agent creation templates are inventoried and mapped.

Excel ingestion validates sheets, headers, mandatory fields, duplicate keys, and row-level errors.

CRUD operations are request-driven, approval-controlled, and audited.

Access remains the controlled master snapshot; clients do not write directly to the published database.

Fieldglass and NICE IEX outputs are generated or documented with exact manual blockers.

Audit/bitacora events exist for ingestion, validation, approvals, exports, publication, failures, and recovery.

Integration tests, failure tests, UAT notes, and handoff documentation are complete.

# 11. Smartsheet Kanban Import Package

Purpose. The work plan has been converted into a Smartsheet-ready hierarchy so the PM can import the project, move cards across the Kanban, and mark individual subtasks as they are completed.

Import file. Use docs/17_smartsheet_kanban_import.csv. The file contains 80 rows: 20 parent deliverables and 60 executable subtasks, totaling 60 hours across three weeks.

## Recommended Smartsheet setup

Import the CSV as the project sheet and keep Task ID, Parent ID, and Level as visible columns during setup.

Use Parent ID and Level to group each subtask below its deliverable. A deliverable is complete only when all child subtasks are Done.

Use Status as the Kanban status field with these values: Backlog, Ready, In Progress, Code Review / Validation, Testing, UAT, Done, and Blocked.

Add Smartsheet owners and dates during project kickoff; the imported Owner column provides the recommended role, not a named individual.

Use Dependency to connect the sequence. Multiple dependencies are separated with a semicolon.

## Imported field definitions

| Field | Use in Smartsheet | Example |
| --- | --- | --- |
| Task ID / Parent ID | Preserves parent-child hierarchy | D14 / D14.2 |
| Level / Row Type | Identifies deliverables and subtasks | 0 / Deliverable |
| Week / Phase | Supports weekly views and phase filters | 2 / Phase 4-5 |
| Task Name | Card or task title | Apply approved changes |
| Owner | Recommended role for assignment | Developer / Admin |
| Status | Kanban column/status value | Backlog |
| Estimate Hours | Planned effort and capacity tracking | 1.5 |
| Dependency | Predecessor task IDs | D10;D14 |
| Acceptance Criteria | Definition of complete for the row | Output passes validation |
| Milestone / Notes | Weekly checkpoint or PM notes | Week 2 core workflow complete |

## PM completion rule

A deliverable may move to Done only when: all subtasks are marked Done, the acceptance criteria are evidenced, required tests have passed, and any open risk or blocker has an explicit disposition. Items that cannot be completed within the 60-hour MVP remain in the next-phase backlog with an owner and next action.