## Sheet1
Scenario cards
Core identity and ingestion
UAT-001 — Standard employee ingestion | Comments
- Objective: Confirm a valid employee file is accepted, staged, traceable, and visible for review.
- Preconditions: Clean Phase 1 environment; source file owner identified.
- Test data: Valid Master Roster, Roster Lock, AccessNow, and/or RSR rows with required fields.
- Steps: Load each source; inspect import batch; inspect staged record; open reconciliation/report view.
- Expected result: Valid rows are accepted, source and batch are retained, and no downstream write occurs. | PASS
- Actual behavior currently implemented: Master Roster/Roster Lock/AccessNow/RSR staging exists; source-specific validation and quarantine run.
- Pass / failure: Pass if counts, source, batch, and evidence reconcile; fail on silent loss, unexpected promotion, or write.
- Owner / evidence: IAM Data Owner; files, batch IDs, row counts, screenshots, logs.
Status: Ready for UAT.
UAT-002 — Canonical analytical identity resolution from one unambiguous record | Comments
- Objective: Confirm that a single valid source observation can be represented by one internal canonical analytical identity.
- Preconditions: A source record with a unique approved identifier; no authoritative source write capability.
- Test data: New employee with no existing Worker and complete required fields.
- Steps: Stage; reconcile; resolve the match; inspect analytical Worker, identifier, source observation, lineage, and history.
- Expected result: One analytical identity is represented with traceability and no duplicate; no authoritative employee or lifecycle decision is made. | PASS
- Actual behavior currently implemented: Existing promotion paths can create an ACTIVE Worker; this is a future writer concern and must not be used as Phase 1 acceptance.
- Pass / failure: Pass if analytical representation is deterministic and evidenced; fail if the result implies hire, provisioning, or source mutation.
- Owner / evidence: IAM Data Owner / Reviewer; analytical Worker ID, source record, match trace, audit event, evidence export.
Status: Ready for UAT.
UAT-003 — Multiple source records for the same employee | Comments
Objective: Confirm records from multiple sources resolve to One Worker only when identity evidence is sufficient.
Preconditions: Matching identifiers across at least three sources.
- Test data: Same employee with equivalent and non-equivalent identifiers.
- Steps: Ingest; reconcile; inspect match signals, lineage, profile, and discrepancy output.
- Expected result: BUSINESS DECISION REQUIRED — IAM must define which identifiers establish identity and when a conflict blocks resolution. | Cuando hay un cambio, se pasa a cuarentena para revision humana IDs Accessnow: Employee ID = No cambia NUID = No cambia Manual intervention systems/reports: Master Roster Employee Number = No cambia NUID/ logon ID= No cambia. Si llega a cambiar, autoridad es accessnow Roster Lock Vendor employee ID: No cambia, si cambia, Fieldglass es autoridad Fieldglass Buyer reference (NUID) = No cambia. Si llega a cambiar, autoridad es accessnow Worker ID = No cambia. Si hay cambio, Fieldglass es autoridad vendor employee ID = No cambia. Si hay cambio, Fieldglass es autoridad Por cada cambio, cuarentena y revision humana. Y alerta/ banner en el perfil haciendo highlight al cambio
- Actual behavior currently implemented: Strong matches are collected; multiple strong matches create conflict; email/name are fallback signals.
Pass / failure: Pass only after IAM approves Expected resolution for each data combination.
- Owner / evidence: IAM Identity Owner; match trace, conflict record, canonical view.
Status: Blocked by BUSINESS decision.
UAT-004 — Exact duplicate source records | Comments
- Objective: Confirm exact same-source duplicates do not create multiple current profiles.
Preconditions: Duplicate detection enabled.
- Test data: Byte-identical and normalized-identical rows, plus a later correction.
- Steps: Load duplicates; inspect summary; identify current/superseded row; rerun ingestion.
- Expected result: BUSINESS DECISION REQUIRED — define whether newest, latest effective date, or source authority wins.
- Actual behavior currently implemented: Same-source records are grouped by normalized signals; newest created-time record is current and earlier rows superseded.
- Pass / failure: Pass only if approved winner, repeatability, and evidence are demonstrated.
- Owner / evidence: Source Owner; source files, hashes, duplicate report, audit history.
Status: Blocked by BUSINESS decision. | Latest effective date source wins for each field accprding to authority defined
UAT-005 — Fuzzy / possible duplicate | Comments
Objective: Confirm near matches are surfaced for human review without an unsafe automatic merge.
Preconditions: Two Workers with similar names/email/identifiers.
- Test data: Same name/different ID; typo; reused email; transliteration; missing identifiers.
- Steps: Ingest; run duplicate report; review candidate; attempt merge only through authorized route.
- Expected result: BUSINESS DECISION REQUIRED — define match score, threshold, evidence, and reviewer decision. | Should follow quarantine process
- Actual behavior currently implemented: No fuzzy score or confidence threshold; canonical candidates are grouped by normalized full name.
- Pass / failure: Pass only if candidate and non-match behavior are approved and repeatable.
- Owner / evidence: IAM Identity Owner; candidate list, match explanation, reviewer decision.
Status: Blocked by BUSINESS decision.
UAT-006 — Conflicting employee status | Comments
- Objective: Confirm status conflicts are identified and resolved according to effective business dates.
- Preconditions: Same person has ACTIVE, DEACTIVATED, and/or TERMINATED records.
- Test data: Conflicting statuses with source timestamps, effective dates, and ingestion order variations.
- Steps: Ingest in different orders; inspect status, discrepancy, and history.
- Expected result: BUSINESS DECISION REQUIRED — define source authority and effective-date precedence.
- Actual behavior currently implemented: Status aliases normalize; rank is ACTIVE, DEACTIVATED, TERMINATED; AccessNow termination rows can override. | ACTIVE, DEACTIVATED, TERMINATED: AccessNow authority and only AccessNow can overwrite
- Pass / failure: Fail if result changes merely because file order changes, unless approved.
- Owner / evidence: IAM Lifecycle Owner; inputs, resulting status, timestamps, audit events.
Status: Blocked by BUSINESS decision.
UAT-007 — Conflicting source profile data | Comments
- Objective: Confirm conflicting names, managers, emails, and identifiers are visible and not silently overwritten.
Preconditions: One matched Worker with Conflicting non-empty source fields.
- Test data: Conflicting manager/name/email/role values and source timestamps.
- Steps: Reconcile; inspect discrepancy; preview update; attempt apply. | First name = Fieldglass Last name = Fieldglass Canonical email: Fieldglass. This should be names TTEC email address Add: KP Email address = AccessNow Employment status: AccessNow Consolidated View Vendor: (Company Name) Accessnow Job title: AccessNow Line of business: Roster Lock Program: Roster Lock Project: Roster Lock Country: Fieldglass (Worker's Physical Location) Site/location: Fieldglass (Location/Location Details) Supervisor: Master Roster (TTEC Sup) Onboarding date = start date fieldglass End date = end date in fiedlglass Engagement status: Unknown NPN: Roster Lock License state: Roster Lock License number: Roster Lock Taxonomy code: Roster Lock Key billable funtion: Roster Lock | Miguel explained that this is the "second step" of UAT-003. In UAT-003, the change does not proceed. If the change were to proceed, a new profile would be created instead. UAT-007 covers the scenario where an exception is accepted for the same employee. UAT-007 focuses on secondary identifiers and how they are handled when linking information to an existing employee rather than creating a new one.
- Expected result: BUSINESS DECISION REQUIRED — define field-level precedence and approval requirement.
- Actual behavior currently implemented: Conflicting RSR profiles are excluded from automatic apply; source update preview shows deltas and usually preserves populated canonical fields
- Pass / failure: Pass if every field has an approved disposition and no silent loss.
- Owner / evidence: IAM Data Owner; discrepancy, preview, decision note, before/after.
Status: Blocked by BUSINESS decision.
UAT-008 — Missing required fields | Comments
Objective: Confirm incomplete records are rejected/quarantined with actionable reasons.
- Preconditions: Quarantine and import audit available.
- Test data: Missing Employee Number, name, source key, invalid status, malformed date, blank identifiers.
- Steps: Load each variant; inspect batch result, quarantine, error reason, and retry behavior.
- Expected result: Invalid data is not promoted; the failed row and reason are recoverable.
- Actual behavior currently implemented: Required-field checks and quarantine exist at source boundaries.
- Pass / failure: Pass if no silent drop and retry does not duplicate valid rows. | Quarantine manual entry files
- Owner / evidence: Source Owner; rejected file, row-level reason, batch log.
- Status: Ready for UAT (source-specific field list still needs confirmation).
UAT-009 — Unknown source observation | Comments
- Objective: Confirm an unknown source observation is surfaced as an analytical unmatched finding/candidate and is not treated as an authoritative employee.
Preconditions: source record has no Worker match.
- Test data: Valid-looking new RSR/AccessNow record and an unauthorized/ambiguous record.
- Steps: Stage; inspect unmatched finding; inspect candidate evidence, lineage, and audit; verify no authoritative action is available.
- Expected result: Unmatched evidence remains visible as INSUFFICIENT_EVIDENCE or another approved finding; no hire/reject/provisioning action occurs.
Actual behavior currently implemented: RSR unmatched records can be promoted into an ACTIVE Worker through an existing writer path; that path is DEFERRED-PHASE2_WRITER
- Pass / failure: Pass if only an analytical finding/candidate exists; fail on automatic or authoritative creation. | Quarantine source records no matched
- Owner / evidence: IAM Identity Owner; unmatched record, match trace, finding, source lineage.
Status: Blocked by technical dependency.
UAT-010 — Employee outside standard roster flow | Comments
- Objective: Determine how contractors, transfers, exceptions, and non-standard workers enter reconciliation.
- Preconditions: Business examples and ownership assigned.
Test data: At least one non-standard onboarding case.
- Steps: Submit through available intake; attempt matching, exception, and export.
- Expected result: BUSINESS DECISION REQUIRED — define eligibility, owner, identifiers, and route. | Role change owner: FG
Actual behavior currently implemented: No complete non-standard onboarding policy.
- Pass / failure: Pass only when a documented route and expected output exist. | Alert on employee profile and home page
- Owner / evidence: IAM Process Owner; approved exception procedure and resulting record.
Status: Blocked by Business decision.
Lifecycle and reconciliation
UAT-011 — Rehire within 30 days | Comments
- Objective: Confirm the same person is treated as a rehire, not an accidental new identity, within the approved window.
- Preconditions: Inactive AccessNow worker and matching Roster Lock row.
- Test data: Termination and roster dates at 0, 1, 29, and 30 days, including holidays.
- Steps: Ingest; run alert; inspect elapsed-day calculation, matching, status, and archive action.
- Expected result: BUSINESS DECISION REQUIRED — calendar/business days and boundary rules are unresolved. | Business days, holidays should not affect business days count
- Actual behavior currently implemented: Inclusive 0–30 business-day alert; weekdays only; optional holiday list; fallback to created timestamps if dates missing.
- Pass / failure: Pass only after date semantics are approved and boundary cases agree.
- Owner / evidence: IAM Lifecycle Owner; dates, calendar, alert, resulting Worker/engagement.
Status: Blocked by Business decision.
UAT-012 — Rehire after 30 days | Comments
Objective: Confirm a rehire beyond the window follows the approved identity/engagement rule.
- Preconditions: Same person with prior inactive Worker and later source record.
- Test data: 31 business days, 31 calendar days, and materially later rehire.
- Steps: Ingest; reconcile; inspect match, engagement, and notification.
- Expected result: BUSINESS DECISION REQUIRED — define whether prior Worker is reused, new engagement added, or new Worker proposed. | Prior worker profile should be reused/updated
- Actual behavior currently implemented: Rehire alert only handles the 0–30 business-day window; broader lifecycle policy is absent.
- Pass / failure: Fail if system silently creates or merges without approved rule.
- Owner / evidence: IAM Lifecycle Owner; match trace, engagement history, decision.
Status: Blocked by BUSINESS DECISION
UAT-013 — No-hire employee | Comments
- Objective: Confirm a no-hire/blacklist record prevents or quarantines onboarding as intended.
- Preconditions: Approved test no-hire record and safe test environment.
- Test data: Exact match, possible match, expired entry, and override case.
Steps: Ingest onboarding record; observe match, quarantine, alert, and export behavior.
Expected result: BUSINESS DECISION REQUIRED — key, expiry, override, and enforcement point must be defined. | correct result: business decision pending
Actual behavior currently implemented: no complete no-hire enforcement was found.
- Pass / failure: Not passable until the rule is implemented and approved.
- Owner / evidence: IAM Compliance/Lifecycle Owner; protected test data, decision, outcome. | Owner: Dana
- Status: Not implemented | Will be move to backlog due to peding input for owner
UAT-014 — Employee present in one source but missing from another | Comments
Objective: Confirm missing cross-source coverage becomes a discrepancy with correct ownership.
Preconditions: Two source snapshots with intentionally missing person.
- Test data: Worker in AccessNow only, Roster Lock only, RSR only, and Master Roster only.
- Steps: Load snapshots; run reconciliation/report; inspect discrepancy and export inclusion.
- Expected result: BUSINESS DECISION REQUIRED — define which absence is exceptional and expected resolution time. | exception master roster
- Actual behavior currently implemented: Reports expose source coverage and open discrepancies; no full policy/SLA was found. | No SLA at the moment
- Pass / failure: Pass only if discrepancy type, severity, owner, and export treatment are approved.
- Owner / evidence: IAM Data Owner; snapshots, coverage report, discrepancy assignment.
Status: Blocked by Business decision. | Alert on employee profile and home page
UAT-015 — Source conflict and field-level classification | Comments
- Objective: Confirm a conflicting field is classified as authority, discrepancy, expected difference, source latency, or insufficient evidence only when evidence supports it.
Preconditions: Same Worker with conflicting source values.
- Test data: Conflicting names, manager, email, and dates by source.
- Steps: Reconcile; generate canonical/report/export views; compare selected values.
- Expected result: Without an approved field-level authority rule, both observations remain visible as DISCREPANCY, EXPECTED_DIFFERENCE, SOURCE_LATENCY, or | Alert on employee profile and home page
INSUFFICIENT_EVIDENCE; the platform does not silently overwrite evidence. | Onboarding date = start date fieldglass . Puede cambiar, fiedlglass es la autoridad End date = end date in fiedlglass. Puede cambiar, fiedlglass es la autoridad | This test compares the timing of updates between systems. If a change appears in the Master Roster before it appears in another platform, the difference may be expected for a defined period. During that time, it is treated as Source Latency rather than a discrepancy. The goal is to verify whether all platforms become aligned within the agreed timeframe.
- Actual behavior currently implemented: Report engagement preference uses Roster Lock > RSR > AccessNow plus completeness/recency; this is an encoded heuristic, not an
approved universal winner.
- Pass / failure: Pass if the classification and evidence are consistent; fail if an unapproved source silently wins.
- Owner / evidence: IAM Data Owner; precedence matrix, report, export, audit. | Sophie/automate
Status: Blocked by Business decision.
UAT-016 — Source freshness, latency, and timestamp conflict | Comments
- Objective: Confirm stale and current records are handled predictably.
- Preconditions: Source records with different created, updated, effective, and received timestamps.
Test data: Late-arriving correction, stale active record, future-dated change, missing timestamp. | Automation owner: Sophie
- Steps: Load in varying order; compare canonical/report/history output. | RosterLock-on demand updates only / Mater Roster-weekly update / FG-on demand or daily? / AccessNow daily
- Expected result: Snapshot date, effective date, received/imported date, and data age remain distinct; a mismatch is SOURCE_LATENCY until the approved window expires, not
automatically a discrepancy.
- Actual behavior currently implemented: Some paths use created time, updated time, or effective fields; no global policy found — ASSUMPTION CURRENTLY ENCODED.
- Pass / failure: Pass if results expose temporal evidence and approved latency semantics; fail if load order alone creates a business conclusion.
- Owner / evidence: IAM Data Owner; timestamps, run order, selected value, history. | Sophie/automate
Status: Blocked by Business DECISION
UAT-017 — Historical identity records | Comments
- Objective: Confirm old identifiers, names, engagements, and profile versions remain searchable and traceable.
- Preconditions: Worker with at least two profile versions and an old identifier.
Test data: Name change, identifier change, rehire engagement, superseded source row.
- Steps: Inspect current view, history, lineage, and audit; search using current and historical identifier.
- Expected result: Historical evidence is retained and current identity is distinguishable. | PASS
- Actual behavior currently implemented: Immutable profile versions, identifiers, engagements, lineage, and snapshots exist.
- Pass / failure: Pass if no history is deleted or confused with current value.
- Owner / evidence: IAM Audit/Data Owner; history export, lineage, screenshots.
Status: Ready for UAT.
UAT-018 — Employee identifier change | Comments
- Objective: Confirm an identifier change updates history without splitting or merging the wrong Worker.
- Preconditions: Existing canonical Worker and approved source correction.
- Test data: Changed Employee Number/NUID/NPN/email, reused old value, and conflicting new value. | Employee Number/NUID/NPN : NEVER CHANGE
- Steps: Ingest; review match; inspect identifier history and duplicate candidates.
- Expected result: BUSINESS DECISION REQUIRED — define which identifier changes preserve identity and required approval. | Alert on employee profile and home page
- Actual behavior currently implemented: Identifier history model exists; matching aliases may treat IDs as equivalent.
- Pass / failure: Fail on silent split/merge or loss of old identifier.
- Owner / evidence: IAM Identity Owner; old/new identifiers, decision, history.
Status: Blocked by Business DECISION
UAT-019 — Name change | Comments
- Objective: Confirm a legitimate name change does not create a duplicate.
- Preconditions: Worker with strong stable identifier and changed name.
Test data: Legal Name change, typo correction, Same Name/different person.
- Steps: Ingest; reconcile; inspect current profile, history, and duplicate report.
- Expected result: BUSINESS DECISION REQUIRED — define proof and precedence for name changes. | Alert on employee profile and home page
- Actual behavior currently implemented: Exact name is a fallback signal; history supports versioning; source updates generally avoid overwriting populated fields.
- Pass / failure: Pass only if business-approved identity key and update path are followed.
- Owner / evidence: IAM Identity/Data Owner; source proof, profile versions, discrepancy.
Status: Blocked by Business decision. | Employee identity identifiers matched and name change is reflecting on AccessNow and FG, proceed with the change, NO business decision needed, Add an identifier that name was change
UAT-020 — Manager change | Comments
- Objective: Confirm manager changes are visible, dated, and attributed to the correct source. | AccessNow Manager : IAM manager MasterRoster Supervisor: Vendor manager
- Preconditions: Existing Worker with manager in one or more sources.
Test data: Valid change, conflicting change, manager unavailable, circular hierarchy.
- Steps: Load; inspect delta preview, canonical/report output, history, and export.
- Expected result: BUSINESS DECISION REQUIRED — define authority, effective date, and hierarchy validation. | Alert on employee profile and home page, if there is a change in Access Now or Master Roster apply the change and show a banner for 2 weeks
- Actual behavior currently implemented: Source update preview and profile deltas exist; no final manager policy found.
- Pass / failure: Fail on silent overwrite or undated change.
- Owner / evidence: IAM Data Owner; before/after, source timestamp, approval. | Sophie/automate
Status: Blocked by Business decision. | Ready for implementation
UAT-021 — Role/access change request (deferred writer scenario) | Comments
Objective: Distinguish a recorded request from an Actual downstream access change.
- Preconditions: Requester/reviewer accounts; downstream sandbox if required.
- Test data: Create, update, deactivate, and role-change requests.
- Steps: Submit and approve request; inspect status, publication queue, and downstream result.
- Expected result: DEFERRED — PHASE2_WRITER. Phase 1 may report a role/access observation or finding only; it does not approve, apply, or execute the change. | BACKLOG
- Actual behavior currently implemented: Request operations and approval/publication structures exist; downstream live integrations are future.
- Pass / failure: Fail if UAT claims access changed when only a request/export exists.
- Owner / evidence: IAM Process Owner; request JSON, approval, queue, downstream handoff.
- Status: Deferred — PHASE2_WRITER; does not block Phase 1.
UAT-022 — Deactivated employee | Comments
- Objective: Confirm deactivation is visible and does not get undone by stale active data.
Preconditions: Worker with deactivation/termination evidence
- Test data: Deactivated person with later stale ACTIVE row and no later effective event.
- Steps: Ingest; reconcile; inspect status, report, export eligibility, and alert.
- Expected result: BUSINESS DECISION REQUIRED — source authority and timing.
- Actual behavior currently implemented: Status normalization/ranking exists; AccessNow termination handling exists. | Autority is AccessNow
- Pass / failure: Fail if stale active row silently wins.
- Owner / evidence: IAM Lifecycle Owner; dates, status history, output.
Status: Blocked by Business decision.
UAT-023 — Reactivated employee | Comments
- Objective: Confirm reactivation requires the correct evidence and preserves prior history.
- Preconditions: Terminated/deactivated Worker and later active record.
- Test data: Authorized reactivation, accidental active feed, and rehire case.
- Steps: Ingest; inspect match, status, engagement, and audit.
- Expected result: BUSINESS DECISION REQUIRED — distinguish reactivation from rehire and define proof. | Alert on employee profile and home page
- Actual behavior currently implemented: Active status can rank above deactivated/terminated; no dedicated reactivation policy found. | If there is a reactivation in FG and AccessNow employee shoud be reactivate
Pass / failure: Fail on silent reactivation.
- Owner / evidence: IAM Lifecycle Owner; source evidence, decision, engagement history.
Status: Blocked by Business decision. | Phase 2: This should be cross-checked with no higher policy.
Outputs, security, and operations
UAT-024 — Analytical evidence export generation | Comments
- Objective: Confirm authorized users can generate the required Phase 1 reports and evidence exports.
- Preconditions: Approved test data; export directory; authorized role.
- Test data: Workers with complete, incomplete, duplicate, conflict, inactive, and historical records.
- Steps: Generate canonical/reconciliation and evidence exports; inspect naming, format, population, and audit.
- Expected result: Export completes, has stable schema, and does not write live downstream systems. | PASS
- Actual behavior currently implemented: Report service provides analytical report output; Salesforce-specific export is documented separately as future integration.
- Pass / failure: Pass if format, scope, and authorization meet signed specification.
- Owner / evidence: IAM Data/Reporting Owner; files, checksums, row counts, audit event.
- Status: Ready for UAT (business format/sign-off still required)
UAT-025 — Export completeness | Comments
- Objective: Confirm every eligible canonical Worker appears exactly once and exceptions are accounted for.
Preconditions: Reconciled fixture with known Expected population.
- Test data: Full fixture plus unmatched, quarantined, duplicate, inactive, and missing-source cases.
- Steps: Generate export; reconcile row count and IDs to expected population; inspect exclusions. |  | This one gets complete when we pass 003,007 and 0015
- Expected result: BUSINESS DECISION REQUIRED — define eligible population and treatment of exceptions/inactive workers.
- Actual behavior currently implemented: Reports target one row per canonical Worker; Salesforce-specific request export is deferred and not used for Phase 1 completeness.
- Pass / failure: Fail on unexplained omission, duplicate, or inclusion.
- Owner / evidence: IAM Data Owner; control totals, exception list, exported IDs.
Status: Blocked by Business decision.
UAT-026 — Audit trail for Phase 1 platform actions | Comments
- Objective: Confirm ingestion, reconciliation, finding review, evidence export, analytical snapshot publication, and recovery events are attributable.
- Preconditions: Audit logging enabled; test users with distinct roles.
- Test data: One successful and one failed action in each Phase 1 flow.
- Steps: Execute actions; query JSONL audit; compare actor, entity, before/after, result, error, correlation ID.
- Expected result: Required Phase 1 platform actions have actor, entity, result, evidence, and correlation data; retention, immutability, required event catalog, and access remain |  | Explicacion de Miguel: O sea, esto es ya tiene que estar en producción en modo solo solo lectura que tiene que tener un administrador y se puede auditar el acceso. O sea, esto es como que ya la fase uno pasó, pero no ha pasado. Hasta que todos los de arriba no se no se validen, este todavía no se puede validar.
BUSINESS DECISION REQUIRED.
- Actual behavior currently implemented: Append-oriented daily JSONL includes the listed fields; cryptographic immutability/retention are not complete.
- Pass / failure: Fail on missing actor, outcome, or correlation for a material action.
- Owner / evidence: IAM Audit/Compliance Owner; audit files, event IDs, retention proof.
Status: Blocked by Business decision.
UAT-027 — Authoritative mutation prevention | Comments
- Objective: Prove Phase 1 technically prevents authoritative lifecycle mutation while allowing internal analytical/runtime mutation.
- Preconditions: Production-like deployment, read-only role, administrator role, and audit access.
- Test data: Existing Worker and source records.
- Steps: Attempt hire/reject, terminate/reactivate, provision/deprovision, source-platform writes, automatic business decisions, and direct API mutation; separately verify ingestion,
reconciliation, lineage, review state, evidence, snapshot publication, and restore.
- Expected result: Authoritative business mutation is technically impossible from Phase 1. Analytical/technical mutation is permitted. Technical publication of the read-only analytical
database is not business-change publication.
- Actual behavior currently implemented: Routes exist for promotion, apply, merge, approval, publish, and restore; architecture says read-only. This is a repository contradiction
requiring a gate/composition boundary, not a Phase 1 business decision.
- Pass / failure: Pass only when no authoritative mutation path is reachable; fail on any source-system write or automatic business outcome. | System alert
- Owner / evidence: IAM Security Owner; permission matrix, API responses, audit, database diff.
Status: Blocked by technical dependency
UAT-028 — Unauthorized user access | Comments
- Objective: Confirm unapproved users cannot log in or access sensitive employee data.
- Preconditions: Approved and unapproved test accounts; production authentication configuration.
Test data: Local account, approved CSV entry, unknown user, expired/Deactivated user.
- Steps: Attempt login and protected route access; inspect denial and audit.
- Expected result: Access follows approved identity provider and role policy; denial is logged without data leakage. | PASS
- Actual behavior currently implemented: Local SQLite login and approved-user CSV exist; development auto-approval defaults true.
- Pass / failure: Pass only in production-like configuration with auto-approval disabled and strong auth verified.
- Owner / evidence: IAM Security Owner; auth config, access matrix, logs.
Status: Ready for UAT in Production-like Security configuration.
UAT-029 — Role-based access | Comments
- Objective: Confirm requester, reviewer, administrator/writer, auditor, and temporary elevation permissions match policy.
- Preconditions: One test user per role and delegation/elevation fixtures.
Test data: actions: view, Submit, review, decide, merge, publish, restore, Export, audit.
- Steps: Execute each action as each role; compare result with approved matrix.
- Expected result: BUSINESS DECISION REQUIRED — role catalog and actual decision authority must be reconciled. | Matrix de roles need to be created
- Actual behavior currently implemented: identity.py and request service restrict decisions to admins; role catalog says reviewer reviews and decides.
- Pass / failure: Fail on role drift or privilege escalation.
- Owner / evidence: IAM Security Owner; matrix, route results, audit.
Status: Blocked by Business decision.
UAT-030 — Recovery / versioned data | Comments
- Objective: Confirm backup, refresh, checksum, restore, and profile-history recovery preserve approved evidence.
- Preconditions: Disposable test copy and known snapshot checksum.
- Test data: Snapshot A, changed Snapshot B, local notifications, audit, and staged records.
- Steps: Publish/refresh; create backup; restore A; verify checksum, workers, history, notifications, and audit.
- Expected result: Restore returns the selected version without silent data loss or cross-user contamination.
- Actual behavior currently implemented: Runtime sync creates backups, uses atomic sync, checksum checks, and restore route.
- Pass / failure: Pass if all required artifacts and version identity are verified.
- Owner / evidence: IAM Operations Owner; checksums, backup manifest, restore log, record counts. | Sophie/automate
- Status: Ready for UAT (retention and local-notification policy still required). | ASK historical data
UAT-031 — Duplicate merge execution (deferred writer scenario) | Comments
- Objective: Confirm an approved merge preserves evidence and makes supersession clear.
- Preconditions: Two candidate Workers; authorized merge role; backup.
- Test data: Matching identity, conflicting profiles, engagements, identifiers, discrepancies, and audit events.
- Steps: Review merge plan; require reason/approval; execute; inspect survivor, superseded Worker, lineage, reports, and history.
- Expected result: DEFERRED — PHASE2_WRITER. Phase 1 only presents duplicate candidates and evidence; it does not execute an authoritative merge. | PASS
- Actual behavior currently implemented: Merge route/service exists and preserves evidence, but automatic merge is not authorized and read-only scope conflicts.
- Pass / failure: Fail on unapproved merge or broken references.
- Owner / evidence: IAM Identity/Audit Owner; plan, approval, before/after IDs, backup.
- Status: Deferred — PHASE2_WRITER; does not block Phase 1.
UAT-032 — Manual review / exception handling | Comments
- Objective: Confirm conflicts, unmatched rows, quarantine, and overdue items have an owner, status, reason, and disposition.
- Preconditions: Reviewer and administrator test users; exception fixtures.
- Test data: Quarantined row, conflict, unmatched observation, duplicate candidate, source-latency finding, and policy-relevant finding.
- Steps: Open exception; assign/review; record decision; resolve/reject/escalate; inspect history and notification.
- Expected result: BUSINESS DECISION REQUIRED — define SLA, owners, dispositions, and escalation. | Quarentine SLA: 3bd // Admin: Owner and Escalation
- Actual behavior currently implemented: Quarantine, under-review, rejected, conflict, and overdue notification paths exist, but policy is incomplete. | Should go to admin queue to pending items with SLA notification
- Pass / failure: Fail on orphaned or silently resolved exception.
- Owner / evidence: IAM Operations Owner; exception ID, assignment, decision note, audit.
Status: Blocked by Business decision.
UAT-033 — Salesforce evidence export boundary (deferred) | Comments
- Objective: Confirm the future Salesforce-format file is an evidence/handoff export and not live Salesforce provisioning.
- Preconditions: Future-phase export template and Salesforce sandbox contact.
Test data: approved Create/update requests, duplicate Employee requests, missing mapping fields.
- Steps: Generate XLSX; validate mappings, latest-request selection, alias/federation values, and manual handoff.
- Expected result: DEFERRED — FUTURE_INTEGRATION. Any future Salesforce file must be a reproducible handoff; no Salesforce API write or account decision occurs. Template | HOLD- PHASE 2
mappings/defaults require separate validation.
- Actual behavior currently implemented: Export-only XLSX; no Salesforce API/authentication; default country/timezone/locale and generated alias/federation mapping.
- Pass / failure: Fail if consumers expect live provisioning or reject mappings.
- Owner / evidence: Salesforce Owner + IAM Reporting Owner; file, mapping sign-off, handoff receipt.
- Status: Deferred — FUTURE_INTEGRATION; does not block Phase 1.
UAT-034 — Future integration boundaries | Comments
- Objective: Confirm future AD/Azure, CXOne, NICE, SQL, orchestrator, and ITSM integrations are excluded or separately accepted.
- Preconditions: Phase scope and handoff owners documented.
Test data: one record for each future integration boundary.
- Steps: Attempt to locate live connector, execute export/handoff, record actual endpoint and owner.
- Expected result: DEFERRED — FUTURE_INTEGRATION. Phase 1 has no live write; each future dependency is separately owned and must not block Phase 1 sign-off. | HOLD- PHASE 2
- Actual behavior currently implemented: Requirements and README describe integrations as future/placeholders; live ITSM writes are not evident.
- Pass / failure: Fail if undocumented live side effects exist or a required handoff has no owner.
- Owner / evidence: IAM Solution Owner; architecture, connection inventory, handoff evidence.
- Status: Deferred — FUTURE_INTEGRATION; does not block Phase 1.
UAT-035 — Local versus global notifications | Comments
- Objective: Confirm operational alerts stay with the local user and only database publication creates a global signal.
Preconditions: Two Local users/computers, shared publication folder, notification fixtures.
Test data: ingestion error, discrepancy, source-latency finding, analytical database publication, repeated publication within five minutes.
- Steps: Trigger each event; inspect each local notification store and shared folder; repeat publication.
- Expected result: Local events are not visible to another user; publication signal is global, critical, and throttled to five minutes. | PASS
- Actual behavior currently implemented: Local operational JSON store under .iam_notifications; shared DATABASE_SNAPSHOT_PUBLISHED signal with five-minute throttle.
- Pass / failure: Fail on cross-user operational noise, DB persistence, or excessive publication signals.
- Owner / evidence: IAM Operations Owner; per-user files, shared signal, timestamps.
Status: Ready for UAT.
UAT-036 — Analytical snapshot publication and version visibility | Comments
- Objective: Confirm technical publication of a read-only analytical database is authorized, versioned, checksum-checked, and visible to other users only as a global publication event.
- Preconditions: Approved snapshot, publisher role, expected checksum, second user environment.
Test data: Valid Snapshot, stale checksum, concurrent update, repeated publication.
- Steps: Publish; inspect backup, checksum, database version, global notification, and second user refresh.
- Expected result: Only authorized technical snapshot publication succeeds; stale/concurrent publication fails safely; global signal is not duplicated inside five minutes. This is not
business-change publication.
- Actual behavior currently implemented: Publish route requires Application/Master role, uses checksum/concurrency checks, backups, and global signal.
- Pass / failure: Fail on overwrite, unauthorized publish, wrong version, or local operational leakage.
- Owner / evidence: IAM Operations/Security Owner; checksum, backup, route response, notifications.
- Status: Ready for UAT (five-minute policy confirmation required)